## Sheet1
ID | Category | Area | Change Required | Expected Outcome | Priority | Status | Comments
BR-01 | Branding | Company Branding | Replace placeholder branding with the official Excelra logo throughout the course. | Consistent branding across all digital learning courses. | Medium | Not Started
LG-01 | Login & Access | Login Experience | Remove the login page for production deployment. Learners should launch directly from the organization portal. | Simplify learner onboarding. | High | Not Started
SEC-01 | Security | Developer Tools | Disable F12, Ctrl+U, right-click and browser inspection tools. | Reduce the possibility of bypassing course logic. | High | Not Started
UI-01 | User Interface | Button Design | Reduce the size and visual dominance of navigation buttons. | Cleaner and more balanced interface. | Low | Not Started
UI-02 | User Interface | Readability | Improve font contrast and readability wherever text blends into the background. | Better learner experience. | Medium | Not Started
NAV-01 | Navigation | Help Screen | Introduce a Help / How to Use screen explaining navigation, icons, controls and learner expectations before the course begins. | Reduce learner confusion. | High | Not Started
NAV-02 | Navigation | Sequential Flow | Ensure learners always follow the intended sequence instead of jumping across modules. | Maintain instructional flow. | High | Not Started
NAV-03 | Navigation | Resume Learning | Resume learners from their last completed location after refresh or browser closure. | Improve learning continuity. | High | Not Started
NAV-04 | Navigation | Progress Indicators | Clearly distinguish Not Started, In Progress and Completed modules using visual indicators. | Better progress visibility. | Medium | Not Started
VID-01 | Videos | Playback Controls | Prevent forward seeking while allowing rewind. | Ensure genuine content consumption. | High | Not Started
VID-02 | Videos | Full Screen | Fix play/pause behaviour while in full-screen mode. | Improve playback experience. | Medium | Not Started
VID-03 | Videos | Synchronization | Ensure narration always matches the content displayed on screen. | Improve comprehension. | High | Not Started
LD-01 | Learning Design | Module Completion | Do not mark modules complete unless the learner watches the required percentage or explicitly completes the activity. | Accurate completion tracking. | High | Not Started
LD-02 | Learning Design | Learner Guidance | Clearly explain what learners should do before each activity. | Better learner orientation. | Medium | Not Started
ASM-01 | Assessment | XP Logic | Correct XP calculation across quizzes and games. | Reliable scoring. | High | Not Started
ASM-02 | Assessment | Completion Logic | Prevent activities from being marked complete unless genuinely completed. | Maintain assessment integrity. | High | Not Started
ASM-03 | Assessment | Progress Validation | Ensure certification eligibility is based on actual completion rather than navigation. | Accurate certification. | High | Not Started
GAME-01 | Gamification | Word Scramble | Fix the issue where the game becomes stuck after incorrect answers. | Stable game experience. | High | Not Started
GAME-02 | Gamification | Drag & Drop | Improve drag-and-drop usability and discoverability. | Easier interaction. | Medium | Not Started
GAME-03 | Gamification | Progress Counters | Ensure counters update correctly and clearly explain their meaning. | Better learner understanding. | Medium | Not Started
PERF-01 | Performance | Video Behaviour | Resolve intermittent playback issues. | Smooth learning experience. | Medium | Not Started
PERF-02 | Performance | Revision Engine | Display revision prompts only when learners actually require revision. | Reduce unnecessary interruptions. | Medium | Not Started
CNT-01 | Content | References | Keep the References section purely informational. Remove assessments from this section. | Clear separation of learning and reference material. | Low | Not Started
CNT-02 | Content | GoStar References | Reduce excessive GoStar-specific references so the course remains broadly applicable. | Improve content neutrality. | Low | Not Started
AUD-01 | Audio | Pronunciation | Correct pronunciation inconsistencies in the narration. | Professional audio quality. | Low | Not Started
UX-01 | User Experience | Timer | Remove the overall session timer if it does not provide learning value. | Cleaner interface. | Low | Not Started
UX-02 | User Experience | Navigation Buttons | Ensure the Next button progresses within a module before advancing to the next module. | More intuitive navigation. | Medium | Not Started
CERT-01 | Certification | Progress Reporting | Show learners exactly which sections remain incomplete instead of only displaying an overall percentage. | Actionable learner feedback. | Medium | Not Started
AI-01 | AI Assistant | Chatbot | Display an instructional message if login is required before chatbot usage. | Better user guidance. | Low | Not Started